## Detail
Colombo District
RIDP/SP (M 20) Programme
Physical and Financial Progress of the Month of JULY- 2018
Division COLOMBO 950
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 780
SN | Code of MP | Project No | Project Name | G.N. Division |  | Electorate Division | Sector | Type of Project |  | Allocation (Rs.) | Total Estimate Cost (Rs.) |  | Amount of Released Allocation (Rs) |  |  | Agreement Cost (Rs) | Physical Progress (c) | [9 empty] | Financial Progress |  |  |  | No of Beneficiaries | Measurement |  | Implementing Agency | CBO/ Contractor | Starting Date | End Date | Remarks
[17 empty] | A | B |  |  |  | C | D | E | F | G | Expenditure (Work Done)(Rs) | Tax (Rs) (Vat , NBT) | Admin Cost (1.5%,0.5%) (Rs) | Total Expenditure (Rs)
|  |  |  | Name | No |  |  | Construction | Puchasing |  | TAX (Rs) (VAT , NBT | Without TAX (Rs) | Without Adm (Rs) | Admin (1.5%/0.5%) (Rs) | Total (Rs) |  |  | i | ii | iii | iv | [10 empty] | Key performance indicator | Value of mesurment
1 | M R | RIDP/SP/M20/COL/2018/01 | Renovation of drains and concreting in 132 watte and 110 watte at panchikawatte road,colombo 10 | Panchikawatta | 38 | C c | RA | 1 |  | 1500000 | 1394766.6 |  | 1382742.75 | 6011.92 | 1388754.67 | 1155250 | [5 empty] | 1 | [11 empty] | D S | Inmec construction | 2018-05-04
2 | M R | RIDP/SP/M20/COL/2018/02 | Colombo 10 Maligawatte Road Construction of the Daana Shalawa of the Boosewana viharaya concrete Foudation for Development Including |  |  |  | PW | 1 |  | 1350000 | [6 empty] | 1 | [16 empty] | D S
3 | M R | RIDP/SP/M20/COL/2018/03 | Renovation of drain system and concreting of 310 watte, wolfendhal street, colombo 13 | Masangasweediya | 21 | NC | RA | 1 |  | 740000 | 739999.47 |  | 733620.16 | 3189.65 | 736809.82 | 617400 | [9 empty] | 1 | [7 empty] | D S | Inmec construction | 2018-05-04
4 | M R | RIDP/SP/M20/COL/2018/05 | Estimate for development of BoundryWall at kotahena sinhala kanishta vidyalaya |  |  |  | OI | 1 |  | 1000000 | 1000000 |  | 991448.28 | 4275.86 | 995724.14 | 827303.25 | [5 empty] | 1 | [11 empty] | D E | Jayasekara construction | 2018-06-21
5 | M R | RIDP/SP/M20/COL/2018/06 | Estimate for construction of pavillion infront of volley ball court at vijayaba vidyalaya | Grandpass south | 23 | C c | OI | 1 |  | 1000000 | 1000000 |  | 991448.28 | 4275.86 | 995724.14 | 842386 | [5 empty] | 1 | [11 empty] | D E | siyasara construction | 2018-06-21
6 | R K | RIDP/SP/M20/COL/2018/07 | Construction of pavement at jampata lane, kotahena | kotahena west | 18 | NC | RA | 1 |  | 1000000 | 999998.01 |  | 91377.34 | 4310.34 | 995637.67 | 828675 | [5 empty] | 1 | [11 empty] | D S | Inmec construction | 2018-05-04
7 | R K | RIDP/SP/M20/COL/2018/08 | Interlock paving at 146 watte, Ramanadan mawatha, kotahena, colombo 13 | kotahena west | 18 | NC | RA | 1 |  | 1000000 | 782047.64 |  | 775305.85 | 3370.89 | 778676.75 |  |  |  | 1 | [14 empty] | D S
8 | R K | RIDP/SP/M20/COL/2018/09 | Concreting of Enterring road to 1/50 houses in pichchamal watte , sammanthranapura, mattakkuliya. | Mattakkuliya | 10 | N C | RA | 1 |  | 1500000 | 1499997.86 |  | 1487066.84 | 6465.51 | 1493532.35 | 1220320 | [5 empty] | 1 | [11 empty] | D S | Inmec construction | 2018-05-04
9 | R K | RIDP/SP/M20/COL/2018/10 | මුවදොර උයන මහල් නිවාස සංකීර්ණයේ ගොඩනැගිලි 04 හිම විදුලි සෝපානය වටා ඇති පියගැට පේළි වල එනමල් තීන්ත සහ ඉමල්ෂන් තීන්ත ආලේප කිරීම , නිවාස සංකීර්ණයේ ඇතුලත ඇති පොදු ස්ථාන වල විදුලි පහන් අලුත්වැඩියාව, ගොඩනැගිලි 04 වටා අලුතින් ආරක්ෂිත විදුලි පහන් සවි කිරිම. | Mahawatta | 13 | NC | RA | 1 |  | 1500000 | [5 empty] | 1500000 | 1 | [16 empty] | C M C
10 | R K | RIDP/SP/M20/COL/2018/11 | Renovation Main hall and stream water drainage system Sangabodhi vidyalaya | Mahawatta | 13 | NC | OI | 1 |  | 1500000 | 1500000 |  | 1487137.93 | 6431.03 | 1493568.97 | 1261785 | [5 empty] | 1 | [11 empty] | D E | siyasara construction | 2018-06-21
11 | R K | RIDP/SP/M20/COL/2018/13 | Renovation of public toilet system at Bonvista flats,Modara | Modara | 11 | NC | PW | 1 |  | 1500000 | 1499999.65 |  | 1487068.62 | 6465.52 | 1493534.13 | 1287876.75 | [5 empty] | 1 | [11 empty] | D S | Jayasekara construction | 2018-05-04
12 | R K | RIDP/SP/M20/COL/2018/14 | Costruction of storm water At G.No.51,ST Marys Lane ,Mattakkuliya,Colombo 15 | Modara | 11 | NC | PW | 1 |  | 1000000 | [7 empty] | 1 | [15 empty] | C M C |  |  |  | Problem
13 | R K | RIDP/SP/M20/COL/2018/15 | Costruction of sewer line At G.No.27 ,ST Marys Lane ,Mattakkuliya,Colombo 15 | Mattakkuliya | 10 | NC | PW | 1 |  | 1000000 | [7 empty] | 1 | [15 empty] | C M C |  |  |  | Problem
14 | R K | RIDP/SP/M20/COL/2018/16 | Interlock paving at 55 watte, 53 watte, 41 watte, sumithramama road, kotahena | Lunupokuna |  | NC | RA | 1 |  | 1500000 | 1499996.68 |  | 1487065.67 | 6465.5 | 1493531.18 | 1254139.5 | [5 empty] | 1 | [11 empty] | D S | Lapan Lapan construction | 2018-05-04
15 | R K | RIDP/SP/M20/COL/2018/17 | Interlock paving at 268 watte, Aluthmawatha, kotahena | Lunupokuna | 15 | NC | RA | 1 |  | 1500000 | 1499999.48 |  | 1487068.45 | 6465.51 | 1493533.97 | 1208280.3 | [9 empty] | 1 | [7 empty] | D S | Moumt city construction | 2018-05-04
16 | F | RIDP/SP/M20/COL/2018/18 | Interlock paving for roads and by roads from 111/1 to 111/37 in 111 watte at Abdhul Hameed street , colombo 12 | Aluthkade East | 28 | CC | RA | 1 |  | 1500000 | 1499985.1 |  | 1487054.19 | 6465.45 | 1493519.65 | 1190540 | [9 empty] | 1 | [7 empty] | D S | Inmec construction | 2018-05-04
17 | F | RIDP/SP/M20/COL/2018/19 | Interlock paving for roads and by roads from main entrance 111/97 in 111 watte at abdull hameed street , colombo 12. | Aluthkade East | 28 | CC | RA | 1 |  | 1500000 | 1499996.46 |  | 1487065.46 | 6465.5 | 1493530.96 | 1197990.4 | [5 empty] | 1 | [11 empty] | D S | Mount construction | 2018-05-04
18 | F | RIDP/SP/M20/COL/2018/20 | Reconstruction of Storm water Drain system with concreting and covering the drainage system and Construction of the drainage system using concreting of 6mm pipes since concrete at 247 waththa,Miraniya Street,Colombo 12 | Aluthkade East | 28 | CC | RA | 1 |  | 1000000 | 1000000 | [5 empty] | 1 | [16 empty] | C M C |  |  |  | Problem
19 | F | RIDP/SP/M20/COL/2018/21 | Renovation of 04 Toilets and 03 Bathrooms and Interiock paving for the pathways in 189 watte , miraniya street , colombo 12 | Aluthkade East | 28 | CC | PW | 1 |  | 1000000 | 966695.51 |  | 958361.93 | 4166.79 | 962528.72 | 833267.1 | [5 empty] | 1 | [11 empty] | D S | Gunamuthu Bilders | 2018-06-03
20 | F | RIDP/SP/M20/COL/2018/22 | Prepairing Toiles (04 Nos) and bath (03 NOS) & Costruction of sewer line at G.No. 257 Meeraniya street , colombo 12 | Aluthkade East | 28 | CC | PW | 1 |  | 1500000 | [7 empty] | 1 | [15 empty] | D S |  |  |  | Problem
21 | F | RIDP/SP/M20/COL/2018/23 | Costruction of sewer manholes At G.No. 75 Abdhul Hameed Street | Aluthkade East | 28 | CC | RA | 1 |  | 1500000 | [6 empty] | 1 | [16 empty] | C M C
22 | S N | RIDP/SP/M20/COL/2018/24 | Renovation of public toilets and bathrooms in 185,35,38,28,103,84 watte at Jinthupitiya Division | Kochchikade south | 30 | CC | PW | 1 |  | 1500000 | 1499999.09 |  | 1487068.06 | 6465.51 | 1493533.58 | 1293102.66 | [6 empty] | 1 | [10 empty] | D S | Jayasekara construction | 2018-06-03
23 | S N | RIDP/SP/M20/COL/2018/25 | Fixing Street Light Post for comon wathu | Jinthupitiya | 20 | CC | RA | 1 |  | 1500000 | [6 empty] | 1 | [16 empty] | C M C
24 | S N | RIDP/SP/M20/COL/2018/26 | concreting renovation of toilets and bathroom in 168,128,156,125,151 watte and concreting and renovation of drain in 42 watte | Kochchikade south | 30 | CC | PW | 1 |  | 1500000 | [6 empty] | 1 | [16 empty] | C M C |  |  |  | Problem
25 | S N | RIDP/SP/M20/COL/2018/27 | Concreting ,Renovation of staircase renovation of toilets and fixing of gates at tha entrnce of watte in 100,112,176,watte at jampata street colombo 13. 127,39 watte in sangamitta mawatha 80,90,106 watte in vivekananda kandha road 173 watte in Aduruppu street . | Kochchikade south | 30 | CC | PW | 1 |  | 1500000 | 1499999.47 |  | 1487068.44 | 6465.51 | 1493533.96 |  |  |  | 1 | [14 empty] | D S
26 | M G | RIDP/SP/M20/COL/2018/28 | Construction of 02 Nos.Toilets.01 No.washroom 151 Watte Using of Family 103 Jampettha street, colombo 13 | kotahena west | 18 | NC | PW | 1 |  | 504500 | 480815.41 |  | 476670.45 | 2072.48 | 478742.93 |  |  |  | 1 | [14 empty] | D S
27 | Mano Ganeshan | RIDP/SP/M20/COL/2018/29 | Construction of Front side Lunch Room 151 Watte Using of Family 103 Jampettha street, colombo 13 ( reception Hall - First Floor) | kotahena west | 18 | NC | PW | 1 |  | 1449500 | 1064095.1 |  | 1054921.87 | 4586.61 | 1059508.49 |  |  |  | 1 | [14 empty] | D S
28 | M G | RIDP/SP/M20/COL/2018/30 | Construction of Inner side Sport Room 151 Watte Using of Family 103 Jampettha street, colombo 13 ( reception Hall - Ground Floor) | kotahena west | 18 | NC | PW | 1 |  | 1330000 | 1499999.1 |  | 1487068.07 | 6465.51 | 1493533.58 |  |  |  | 1 | [14 empty] | D S
29 | M G | RIDP/SP/M20/COL/2018/31 | Construction of 02 Nos.Toilets.01 washroom and Store room 151 Watte Using of Family 103 Jampettha street, colombo 13 ( reception Hall - Ground Floor) | kotahena west | 18 | NC | PW | 1 |  | 1165500 | 1337561.2 |  | 1326030.5 | 5765.35 | 1331795.85 |  |  |  | 1 | [14 empty] | D S
30 | M G | RIDP/SP/M20/COL/2018/32 | Construction of community Hall 151 Watte Using of Family 103 Jampettha street, colombo 13 ( reception Hall - first Floor) | kotahena west | 18 | NC | PW | 1 |  | 1478400 | 1182366.49 |  | 1172173.68 | 5096.4 | 1177270.08 |  |  |  | 1 | [14 empty] | D S
31 | M G | RIDP/SP/M20/COL/2018/33 | Construction of 02 Nos.Toilets.01 No.washroom 151 Watte Using of Family 103 Jampettha street, colombo 13 ( reception Hall - first Floor) | kotahena west | 18 | NC | PW | 1 |  | 1100800 | 1052157.42 |  | 1043087.1 | 4535.16 | 1047622.26 |  |  |  | 1 | [14 empty] | D S
32 | M G | RIDP/SP/M20/COL/2018/34 | Construction of first floor and renovation work in community hall s at blouemendhal flat | Mattakkuliya | 10 | NC | PW | 1 |  | 1430700 | 1430699.64 |  | 1418366.02 | 6166.81 | 1424532.83 |  |  |  | 1 | [14 empty] | D S
33 | M G | RIDP/SP/M20/COL/2018/35 | preparing and reparing of Gully Lines at 145 Watte Jumma Lane | kotahena west | 18 | NC | RA | 1 |  | 1498100 | [6 empty] | 1 | [16 empty] | C M C |  |  |  | Problem
34 | M G | RIDP/SP/M20/COL/2018/36 | Build 8 Manholes & Cover Slabs at 145 watte,Jumma Lane | kotahena west | 18 | NC | RA | 1 |  | 1481000 | [6 empty] | 1 | [16 empty] | C M C |  |  |  | Problem
35 | M G | RIDP/SP/M20/COL/2018/37 | Building a New Culvert(Bokkuwa) at 77/37,Jakpettah Lane of the main road-Preparing 02 Gulies for two sides | kotahena west | 18 | NC | RA | 1 |  | 1484000 | 936073.6 |  | 928044 | 4034.8 | 932038.8 | [6 empty] | 1 | [11 empty] | C M C
36 | M G | RIDP/SP/M20/COL/2018/38 | Building a New Culvert(Bokkuwa) at 77/37,Jampettah Lane of the main road-Putting Carpet for main Road | kotahena west | 18 | NC | RA | 1 |  | 720000 | 75983.62 |  | 74051.84 | 321.96 | 74373.8 |  |  |  | 1 | [14 empty] | C M C
37 | M G | RIDP/SP/M20/COL/2018/40 | Construction of Basket Ball Court - ST Anthony"s vidyalaya, colombo 13 | kotahena west | 18 | NC | EI | 1 |  | 1985100 | [6 empty] | 1 | [16 empty] | D E
38 | C W | RIDP/SP/M20/COL/2018/41 | Constuction of Public Toilets and construction of side boundry wall and fixing of covering fence on it , at rear premises of St.James Church , Modara | Aluthmawatha | 14 | NC | PW | 1 |  | 1400000 | 1399999.88 |  | 1387930.92 | 6034.48 | 1393965.4 | 1195178.4 | [5 empty] | 1 | [11 empty] | D S | Jayasekara construction | 2018-06-21
39 | C W | RIDP/SP/M20/COL/2018/42 | Costruction of forth flour senior section Roof Top at hairiya vidyalaya | Maligakanda | 40 | CC | EI | 1 |  | 1400000 | [6 empty] | 1 | [16 empty] | D E
40 | R K | RIDP/SP/M20/COL/2018/43 | Concreating of Mahawatta Road 233 watte. | Mahawatta | 13 | NC | RA | 1 |  | 500000 | [6 empty] | 1 | [16 empty] | D S
41 | R K | RIDP/SP/M20/COL/2018/44 | මෝදර ශ්‍රී පඤ්ඤානන්ද මාවත අංක 60/14 යන නිවාස සංකීර්ණෙය් වැසි ජලය බැස යන කාණු පද්ධතියක් සෑදීම | modara | 11 | NC | RA | 1 |  | 500000 | [6 empty] | 1 | [16 empty] | D S
Total | [7 empty] | 41 | 0 | 52017600 | 31843232.48 | 0 | 29676312.7 | 132835.91 | 30709058.68 | 17713494.36 | 12 | 3 | 10 | 0 | 0 | 12 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
** Physical progress
[7 empty] | Description for rating | [11 empty] | Rates |  |  | Percentage Ranges |  |  |  |  | * Projects should be categorized for following sectors
[7 empty] | For Construction Project | [5 empty] | For Puchasing Projects | [13 empty] | Under DCB Programme |  |  |  | Under Rural Infrastructure Development Programme (Special Projects) and 20 Millon
[7 empty] | Estimate is being / to be prepared and initial works started | [5 empty] | Requirements Not Called | [5 empty] | A |  |  | (0 - 5)% |  |  |  |  | WS- Rural Water Supply |  |  |  | WS - Rural Water Supply
[7 empty] | B1 | Estimates approved / Bid documents prepared, |  |  |  |  | B1 | Requirements Called |  |  |  |  | B |  |  | (6 - 25)% |  |  |  |  | EL- Rural Electricity |  |  |  | RA - Rural Access
[7 empty] | B2 | Quotation / Bid called |  |  |  |  | B2 | Requirements Received | [12 empty] | RA- Rural Access |  |  |  | EI - Economic Infrastructure
[7 empty] | B3 | Quotation / Bid Received |  |  |  |  | B3 | Qutation called | [12 empty] | EI- Economic Infrastructure |  |  |  | RE - Rural Economy
[7 empty] | B4 | Contract Awarded. (25% completed) |  |  |  |  | B4 | Estimated prepared | [12 empty] | RW- Rural Welffare |  |  |  | SW- Social Welfare
[27 empty] | CD- Community Development |  |  |  | EL - Rural Electricity
[7 empty] | Constructions : Started construction works , (40% completed) | [5 empty] | Placed orders for goods / instruments | [5 empty] | C |  |  | (26 - 40)% |  |  |  |  | MI- Minor Irrigation |  |  |  | PW - Public Welfare
[27 empty] | SW- Social Welfare |  |  |  | OI - Other Infrastructure
[7 empty] | Constructions : 60% Completed | [11 empty] | D |  |  | (41 - 60)% |  |  |  |  | Under Sukitha purawara
SC -Sanitary and common facilities ( සනීපාරක්ෂක හා පොදු පහසුකම්)
[7 empty] | Constructions : 80% Completed | [5 empty] | Received goods / instruments as per the order | [5 empty] | E |  |  | (61 - 80)% |  |  |  |  | RD - Sanitary and common facilities Road and Derange Development (මාර්ග හා කාණු පද්ධති සංවර්ධනය)
MC -Maternity and Child Clinic ( මාතෘ හා ළමා සායන)
[7 empty] | Constructions : 99% Completed | [5 empty] | Completed lists of goods to be given to beneficiaries | [5 empty] | F |  |  | (81 - 99)% |  |  |  |  | SS - School and Sports (පාසල් හා ක්‍රීඩා සංවර්ධනය)
CH - Community Hall and Sewapiyasa (ප්‍රජා ශාලා හා සේවා පියස ගොඩනැගිලි සංවර්ධනය)
[7 empty] | Constructions : 100% Complete | [5 empty] | Issued goods and instruments to identified institutions/ CBOs | [5 empty] | G |  |  | 100% |  |  |  |  | RP - Religious center Developments (ආගමික මධ්‍යස්ථාන සංවර්ධනය)
[8 empty] | 41 | 0 | 4785100 | 31843232.48 | 0 | 29676312.7 | 132835.91 | 30709058.68 | 17713494.36 | 12 | 3 | 10 | 0 | 0 | 12 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 20 |  | 24773100 | 14696448.3 |  | 12678415.46 | 59036.39 | 13637361.89 | 11334051.2 | 8 |  | 2 |  |  | 7 |  |  |  | 3
Constructions: B - 1 = Estimates approved / Bid documents prepared, B - 2 = Quotation / Bid called B - 3 = Quotation / Bid Received B - 4 = Contract Awarded. (25% completed)

## Summary
Decentralized Capital Budget Programme -2018 - Colombo District
Physical and Financial Progress JULY 2018
| Division | COLOMBO
| Vote | 950
S.No. | Sector | No of Total Projects | Type of Project |  | Allocation (Rs.) | Total Estimate Cost (Rs.) |  | Amount of Released Allocation (Rs) |  |  | Agreement Cost (Rs) | Physical Progress (c) | [9 empty] | Financial Progress |  |  |  | No of Beneficiaries
[12 empty] | A | B |  |  |  | C | D | E | F | G | Expenditure (Work Done)(Rs) | Vat (Rs) | Admin Cost (Rs) | Total Expenditure (Rs)
|  |  | Construction | Puchersing |  | With VAT | Without VAT | Without Adm (Rs) | Admin (1.5%) (Rs) | Total (Rs) |  |  | i | ii | iii | iv
1 | RA | 19 | 19 | 0 | 23423100 | 13428844.52 |  | 11420462.55 | 53567.03 | 12373939.62 | 10172595.2 | 8 | 0 | 2 | 0 | 0 | 6 | 0 | 0 | 0 | 3 |  |  |  |  | 3500
2 | EI | 2 | 2 | 0 | 3385100 | [6 empty] | 2
3 | PW | 17 | 17 | 0 | 21709400 | 14914387.96 |  | 14785815.66 | 64286.13 | 14850101.81 | 4609424.91 | 2 | 2 | 9 | 0 | 0 | 3 | 1 | 0 | 0 | 0
4 | OI | 3 | 3 | 0 | 3500000 | 3500000 |  | 3470034.49 | 14982.75 | 3485017.25 | 2931474.25 | [5 empty] | 3 | [8 empty] | 1500
5
6
Total |  | 41 | 41 | 0 | 52017600 | 31843232.48 | 0 | 29676312.7 | 132835.91 | 30709058.68 | 17713494.36 | 12 | 2 | 11 | 0 | 0 | 12 | 1 | 0 | 0 | 3 |  |  |  |  | 5000
* Projects should be categorized for following sectors
Sukitha purawara
SC - සනීපාරක්ෂක හා පොදු පහසුකම්
RD - මාර්ග හා කාණු පද්ධති සංවර්ධනය
MC - මාතෘ හා ළමා සායන
SS - පාසල් හා ක්‍රීඩා සංවර්ධනය
CH - ප්‍රජා ශාලා හා සේවා පියස ගොඩනැගිලි සංවර්ධනය
RP - ආගමික මධ්‍යස්ථාන සංවර්ධනය

## Sheet1
ග්‍රාමීය යටිතල පහසුකම් වැඩසටහන - මිලි 20 -2018
අනු අංකය | ක්‍රියාත්මක බලධාරී ආයතනය | ව්‍යාපෘති සංඛ්‍යාව | වෙන් කළ මුදල (රු.) | සමස්ත ඇස්තමේන්තුව (රු.) | නිදහස් කල ප්‍රතිපාදන මුදල (රු) | වියදම රු. | භෞතික ප්‍රගතිය |  |  |  |  | ගැටළු
[7 empty] | A | B | C | D | E
1 | ප්‍රාදේශීය ලේකම් (ඉදිකිරීම්) | 25 | 30949400 | 26331175.26 | 26217628.83 |  | 3 | 1 | 9 | 9 | 3 |  | 25
2 | කොළඹ නගර සභාව | 11 | 14183100 | 2012057.22 | 1006412.6 |  | 3 |  | 1 | 1 |  | 6 | 11
3 | ප්‍රාදේශීය ඉංජිනේරු | 5 | 6885100 | 3500000 | 3485017.25 |  | 2 |  |  | 3
| එකතුව | 41 | 52017600 | 31843232.48 | 30709058.68 |  | 8 | 1 | 10 | 13 | 3 | 6
| A - ඇස්තමේන්තු සකස්කරීමට ඇති |  |  | B - ඇස්තාමේන්තු සකස්කර ප්‍රතිපාදන ගෙන්වීමට දි.ලේ යොමුකර ඇති
| C - ප්‍රතිපාදන ලබා ඉදිරි කටයුතු කිරීම |  |  | D -වැඩ ආරම්භකර ඇති
E - වැඩ අවසන්