## Detail
Colombo District
Decentralized Capital Budget Programme
Physical and Financial Progress of the Month of July - 2018
| Division | COLOMBO
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
SN | Code of MP | Project No | Project Name | G.N. Division |  | Electorate Division | Sector | Type of Project |  | Allocation (Rs.) | Total Estimate Cost (Rs.) |  | Amount of Released Allocation (Rs) |  |  | Agreement Cost (Rs) | Physical Progress (c) | [9 empty] | Financial Progress |  |  |  | No of Beneficiaries | Measurement |  | Implementing Agency | CBO/ Contractor | Starting Date | End Date | Remarks
[17 empty] | A | B | [8 empty] | Expenditure (Work Done)(Rs) | Tax (Rs) (Vat , NBT) | Admin Cost (1.5%,0.5%) (Rs) | Total Expenditure (Rs)
|  |  |  | Name | No |  |  | Construction | Puchasing |  | TAX (Rs) (VAT , NBT | Without TAX (Rs) | Without Adm (Rs) | Admin (1.5%/0.5%) (Rs) | Total (Rs) |  |  | i | ii | iii | iv | C | D | E | F | G | [5 empty] | Key performance indicator | Value of mesurment
1 | MR | 2018/DCB/MR/COL/01 | Renovation work and supply and fixing of steel handrail to staircase at the entrance of Badhriya Lane (Secondary road from Panchikawatta road to Mohidheen Masjidh road) Panchikawatta road,Colombo 10 | Panchikawatta | 38 | 950 | RA | 1 |  | 200000 |  | 199988.27 | 194163.37 | 2912.45 | 197075.82 | [18 empty] | DS | bar: B ii
2 | MR | 2018/DCB/MR/COL/02 | Suppyl and fixing of 6' PVC pipe and concreting for the rain water drain system in 211 watte at Jumma Masjidh Road ,Maligawatta,Colombo 10 | Keththarama | 27 | 950 | RA | 1 |  | 500000 |  | 499999.86 | 485436.76 | 7281.558 | 492718.31 | [15 empty] | 475 |  |  | DS | bar: B C
3 | MR | 2018/DCB/MR/COL/03 | Suppyl and fixing of Cover slab,removing of sludge and renovating the drain system at 151 watte,Maligawatta place,Colombo 10 | Keththarama | 27 | 950 | RA | 1 |  | 335000 |  | 333142.69 | 323439.51 | 4851.59 | 328291.1 | [15 empty] | 320 |  |  | DS | bar: B C
4 | MR | 2018/DCB/MR/COL/04 | Development of Safety Boundray wall behind Pathanagara Viharaya,Dematagoda road,Maligakanda,Colombo 10 | Maligawatta |  | 950 | RA | 1 |  | 500000 |  | 499999.07 | 485435.99 | 7281.54 | 492717.53 | [11 empty] | 485435.99 |  | 7281.53 | 492717.52 |  |  |  | DS | 129 Prajasanwardhana Samithiya | 2018.06.18 | 2018.07.02 | bar: B G
5 | MR | 2018/DCB/MR/COL/05 | Constauction work for Second floor of Library Building in Sri Sudharshanarama Viharasthanaya,Maligawatta, Colombo 10 | Maligawatta West | 39 | 950 | CD | 1 |  | 500000 |  | 499999.95 | 485436.85 | 7281.55 | 492718.4 | [15 empty] | 700 |  |  | DS | Sudharmarama Dayaka Sabhawa | bar: B iii
6 | MR | 2018/DCB/MR/COL/06 | Supplying and fixing of cover slabs and Preperation of drain system in C scheme in Maligawatta flat scheme,Colombo 10 | Maligawatta West | 39 | 950 | RA | 1 |  | 300000 |  | 299993.78 | 291256.1 | 4368.84 | 295624.94 | [15 empty] | 370 |  |  | DS | Batahira Gramasanwardana Smithiya | 2018.7.10 | bar: B C
7 | MR | 2018/DCB/MR/COL/07 | Development work in first floor and preperation of staircase in stage at No 132 watte,Panchikawatte,Colombo 10 | Panchikawatta | 38 | 950 | RA | 1 |  | 500000 |  | 499999.88 | 485436.78 | 7281.55 | 492718.33 | [15 empty] | 220 |  |  | DS | bar: B C
8 | MR | 2018/DCB/MR/COL/08 | Development of the Hall at G.No.180 watta,Layards Broad way,Colombo 14 (Attach a power cable,processing plastic windows,concrete the land) | New Bazaar | 22 | 950 | RA | 1 |  | 200000 |  | 145252.42 | [18 empty] | 550 |  |  | CMC | bar: B i
| MR | 2018/DCB/MR/COL/09 | BEAUTI CULTURE TRAING PROGRAMME FOR COLOMBO CENTRAL YOUNG GIRLS. | SEVERAL G.N.DIVISION INCLUDED |  | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 100000 | [6 empty] | 1 | [16 empty] | DS
| MR | 2018/DCB/MR/COL/10 | HAIRSTYLE TRAINING PROGRAMME FOR COLOMBO CENTRAL YOUNG GIRLS. | SEVERAL G.N.DIVISION INCLUDED |  | COLOMBO CENTRAL | SW |  | 1 | 100000 | [6 empty] | 1 | [16 empty] | DS
| MR | 2018/DCB/MR/COL/11 | DRESS MAKING TRAINING PROGRAMME FOR COLOMBO CENTRAL YOUNG GIRL. | SEVERAL G.N.DIVISION INCLUDED |  | COLOMBO CENTRAL | SW |  | 1 | 50000 | [6 empty] | 1 | [16 empty] | DS
| MR | 2018/DCB/MR/COL/12 | Suplly of water filters for registed 58 per schools | all gn |  |  | SW |  | 1 | 350000 | [6 empty] | 1 | [13 empty] | 420 |  |  | DS
| MR | 2018/DCB/MR/COL/13 | Supplying of building materials for development work of dharmanikethanabhiwardhana temple ,no.90 khathtarama mawatha ,colombo 14 | Khathtarama | 27 |  | SW |  | 1 | 1000000 | [6 empty] | 1 | [13 empty] | 360 |  |  | DS
| MR | 2018/DCB/MR/COL/16 | Repair of Staff room at Sir Baron Jayathilaka Vidyalaya,Colombo 10 | Keththarama | 27 | 950 | EI | 1 |  | 250000 |  | 250000 | 242718.45 | 3640.77 | 246359.22 | [15 empty] | 269 |  |  | DE | bar: B ii
10 | MR | 2018/DCB/MR/COL/17 | Reconstruction of science lab at T.B.Jaya Vidyalaya (Zahira), Vithanage Mawatha,Colombo 02 | Wekanda | 43 | 950 | EI | 1 |  | 200000 | [6 empty] | 1 | [16 empty] | DE
11 | MR | 2018/DCB/MR/COL/18 | Accessing the three enclosures of white iron with access to the entrance No.128 in Jithupitiya,Colombo 13. | Jinthupitiya | 20 | 950 | RA | 1 |  | 200000 |  | 199990.85 | [18 empty] | 350 |  |  | DS | bar: B i
12 | MR | 2018/DCB/MR/COL/19 | Development of Main building at Co/Mihindu Maha Vidyalaya,Mihindu Mawatha,Colombo 12 | Keselwatta | 37 | 950 | EI | 1 |  | 250000 | 250000 |  | 243644.07 | 3177.97 | 246822.04 | [15 empty] | 185 |  |  | DE | bar: B ii
| MR | 2018/DCB/MR/COL/20 | SUPPLY OF SPORTS GOODS & EQIPMENT FOR REGISTERED SPORTS SOCIETY IN DIVISIONAL SECRETARIEAT COLOMBO | SEVERAL G.N.DIVISION INCLUDED |  | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 365000 | [6 empty] | 1 | [16 empty] | DS
13 | MR | 2018/DCB/MR/COL/21 | Supplying and fixing of water pump to public water supply tank at 211 watte,Jumma Masjidh flats,Maligawatta,Colombo 10 | Keththarama | 27 | 950 | RW | 1 |  | 75000 |  | 74227.16 | 72065.22 | 1080.97 | 73146.19 | [15 empty] | 155 |  |  | DS | bar: B iii
14 | FM | 2018/DCB/FM/COL/23 | Completion of the remaining work of the Muslim Dhamma School Building in Colombo 12 |  |  | 950 | CD | 1 |  | 200000 | [6 empty] | 1 | [20 empty] | ක්‍රියාත්මක කළ නොහැකි
15 | FM | 2018/DCB/FM/COL/24 | Repairing of 1 and 2 Common Toilets of 227 Watta,Maha Vidyala Mawatha, Colombo 13 | Msangasveediya | 21 | 950 | CD | 1 |  | 300000 |  | 299999.55 | 291261.71 | 4368.92 | 295630.63 | [18 empty] | DS | bar: B ii
16 | FM | 2018/DCB/FM/COL/25 | Development of Rain Water Drainage Systems from K.T. 20 to 47/14 Houses,at 53 watta,Pir Saibu Street,Colombo 12. |  |  | 950 | RA | 1 |  | 300000 | [6 empty] | 1 | [20 empty] | ක්‍රියාත්මක කළ නොහැකි
17 | FM | 2018/DCB/FM/COL/28 | Rehabilitation of drainage system at 50 watta,Tank Road ,Colombo 09 |  |  | 950 | RA | 1 |  | 500000 | [6 empty] | 1 | [20 empty] | ක්‍රියාත්මක කළ නොහැකි
18 | FM | 2018/DCB/FM/COL/29 | Renovation of Drain system from No 198/7/V/2, house to No 198/24/4/A/16 house at 198 watte,Panchikawatte,Colombo 10 | Panchikawatta | 38 | 950 | RA | 1 |  | 500000 |  | 499998.77 | 485435.7 | 7281.53 | 492717.24 | [15 empty] | 301 |  |  | DS | bar: B ii
19 | FM | 2018/DCB/FM/COL/30 | Reconstruction of drainage System at 83 Waththa,Sri Priyadarshana Mawatha,Logatte Lane,Colombo 10 |  |  | 950 | CD | 1 |  | 300000 | [6 empty] | 1 | [20 empty] | ක්‍රියාත්මක කළ නොහැකි
20 | FM | 2018/DCB/FM/COL/31 | Development of Interlocking paving blocks at No 154,Babapulle Place,Colombo 14 | Grandpass South | 23 | 950 | RA | 1 |  | 500000 | [6 empty] | 1 | [16 empty] | DS
21 | FM | 2018/DCB/FM/COL/32 | Development of Interlocking paving blocks at H Block road,Samagi Mawatha,Nawagampura,Colombo 14 |  |  | 950 | RA | 1 |  | 300000 | [6 empty] | 1 | [20 empty] | ක්‍රියාත්මක කළ නොහැකි
22 | CR | 2018/DCB/CR/COL/40 | Completion of the shrine room of Sri Sangha Bhobi Maha Vidyalaya,Mahawatte | Mahawatta | 13 | 950 | EI | 1 |  | 370000 | [6 empty] | 1 | [16 empty] | DE
| CR | 2018/DCB/CR/COL/41 | SUPPLY OF EQIPMENT FOR SIHALA ADHARAYA SOCIETY AG1 KETHARAMA TEMPLE ROAD MALIGAWATTA COLOMBO 10 | MALIGAWATTA |  | COLOMBO CENTRAL | SW |  | 1 | 330000 | [6 empty] | 1 | [16 empty] | DS
23 | CR | 2018/DCB/CR/COL/42 | Reconstruction of children playground at Keththamarama flats,South Grand | Grandpass South | 23 | 950 | CD | 1 |  | 120000 |  | 119960.14 | 116466.16 | 1746.99 | 118213.15 | [15 empty] | 900 |  |  | DS | bar: B ii
24 | RK | 2018/DCB/RK/COL/44 | Supplying Computers to St.James Primary School | Modara | 11 | 950 | EI |  | 1 | 300000 | [6 empty] | 1 | [16 empty] | ZED
25 | RK | 2018/DCB/RK/COL/45 | Interlocking of Open Stage (2nd Stage) at Co/President College,Kotahena | Lunupokuna | 15 | 950 | EI | 1 |  | 590000 | 590000 |  | 575000 | 7500 | 582500 | [15 empty] | 196 |  |  | DE | bar: B ii
26 | RK | 2018/DCB/RK/COL/46 | Recovery nets of the open section of the Common Hall of Sirimuthu Uyana | Mattakkuliya | 10 | 950 | SW | 1 |  | 120000 | [6 empty] | 1 | [13 empty] | 1150 |  |  | DS
27 | RK | 2018/DCB/RK/COL/47 | Repair of the public toilets system at Railway lane,Mahawatte Road | Mahawatta | 13 | 950 | CD | 1 |  | 100000 | [6 empty] | 1 | [16 empty] | DS
28 | RK | 2018/DCB/RK/COL/48 | Paving Interlocking paving blocks in front area at Hamza Vidyalaya - Modara | Aluthmawatha | 14 | 950 | EI | 1 |  | 675000 | 675000 |  | 657838.98 | 8580.51 | 666419.5 | [15 empty] | 800 |  |  | DE | Mount Constraction | bar: B C
29 | RK | 2018/DCB/RK/COL/49 | Repair of common toilets of Bloemandhal Homes | Bloemendhal | 16 | 950 | CD | 1 |  | 500000 |  | 499999.38 | [18 empty] | 120 |  |  | DS | bar: B i
30 | RK | 2018/DCB/RK/COL/50 | Repair of common toilets of Kadjeema watta Homes | Madampitiya | 12 | 950 | CD | 1 |  | 500000 | [6 empty] | 1 | [13 empty] | 300 |  |  | DS
31 | RK | 2018/DCB/RK/COL/51 | Painting electric lifts and unclean buildings at Muwadora Uyana scheme project | Madampitiya | 12 | 950 | CD | 1 |  | 100000 |  | 99990.08 | 97077.75 | 1456.16 | 98533.92 | [18 empty] | DS | bar: B ii
32 | RK | 2018/DCB/RK/COL/54 | Concreting at Nara Institute,Seabrees Garden,Crow Island | Mattakkuliya | 10 | 950 | RA | 1 |  | 500000 | [6 empty] | 1 | [13 empty] | 450 |  |  | DS
33 | RK | 2018/DCB/RK/COL/57 | Renovation work in Statue hall in Modara Church,Bokkuwatte | Modara | 11 | 950 | CD | 1 |  | 400000 |  | 399998.8 | 388348.36 | 5825.22 | 394173.58 | [18 empty] | DS | 528 Prajasanwardhana Samithiya | bar: B C
34 | RK | 2018/DCB/RK/COL/58 | Renovation of Drain system in 95 watte,Modara Street | Modara | 11 | 950 | RA | 1 |  | 400000 |  | 342174.24 | 332208 | 4983.12 | 337191.12 | [18 empty] | DS | 528 Prajasanwardhana Samithiya | bar: B C
| RK | 2018/DCB/RK/COL/60 | SUPPLY OF SPORTS GOODS AND EQIPMENT FOR NAWARALLA SPORTS SOCIETY ,182/30 SRI GUNANANDA MW KOTAHENA COLOMBO 13. | KOTAHENA |  | COLOMBO NORTH | SW |  | 1 | 300000 | [6 empty] | 1 | [16 empty] | DS
| RK | 2018/DCB/RK/COL/61 | SUPPLY OF SPORTS GOODS FOR MAYURA SPORTS SOCIETY 11/F/J, MUWADORA UYANA THOTALAGA, COLOMBO 15. | MAHAWATTA | 13 | COLOMBO NORTH | SW |  | 1 | 300000 | 299490 |  |  |  |  | 299490 | [17 empty] | DS | bar: B i
35 | RK | 2018/DCB/MR/COL/62 | Development of school at St.Anthony's Balika Vidyalaya - Dematagoda | Maligawatta East | 26 | 950 | EI | 1 |  | 250000 | 250000 |  | 243644.07 | 3177.96 | 246822.04 | [15 empty] | 850 |  |  | DE | bar: B ii
36 | RK | 2018/DCB/MR/COL/63 | Reconstruction of Hemamali Balika Maha Vidyalaya,Sri Saddharma Mawatha,Colombo 10 | Maligawatta East | 26 | 950 | EI | 1 |  | 400000 | [6 empty] | 1 | [13 empty] | 862 |  |  | DE
37 | MR | 2018/DCB/MR/COL/64 | Fixing celling in Library area at Dharussalam Vidyalay Colombo 10 | Keththarama | 27 | 950 | EI | 1 |  | 250000 | 250000 |  | 243644.07 | 3177.96 | 246822.03 | [15 empty] | 1250 |  |  | DE | bar: B ii
38 | MR | 2018/DCB/MR/COL/65 | Supplying Loudspeakers and Amplifiers for the Co/ Kalaimagal Tamil Vidyalaya,Sirimavo Bandaranayake Mawatha,Colombo 14 |  |  | 950 | EI |  | 1 | 100000 | [6 empty] | 1 | [16 empty] | ZED
39 | MR | 2018/DCB/MR/COL/66 | Purchase of items and equipments required for WP /CO/ St.Sebastian College | Aluthkade West | 28 | 950 | EI |  | 1 | 200000 | [6 empty] | 1 | [16 empty] | ZED
40 | MR | 2018/DCB/MR/COL/67 | Purchasing of other equipments including computers for the computer lab of the Kathidral (Male) College,Colombo 13 |  |  | 950 | EI |  | 1 | 400000 | [6 empty] | 1 | [16 empty] | ZED
41 | MR | 2018/DCB/MR/COL/68 | Development work (Construction of celling in grade 5 two storied building) at Co/AL - Nassar Vidyalaya | Grandpass North | 24 | 950 | EI | 1 |  | 250000 | 250000 |  | 243644.08 | 3177.96 | 246822.04 | [15 empty] | 850 |  |  | DE | bar: B ii
42 | MR | 2018/DCB/MR/COL/71 | Purchasing of plastic chairs for Al - Hikma Vidyalaya, St.Sebastian Mawatha,Colombo 12 |  |  | 950 | EI |  | 1 | 75000 | [6 empty] | 1 | [16 empty] | ZED
43 | MR | 2018/DCB/MR/COL/72 | Purchase of chairs and tables for WP /Co/ Al Iqbal Girls School at Sir James Peiris Mawatha, Colombo 02 | Wekanda | 43 | 950 | EI |  | 1 | 75000 | [6 empty] | 1 | [16 empty] | ZED
44 | MR | 2018/DCB/MR/COL/73 | Purchase of items and equipments required for WP/Co/ Holly Rosary Tamil Vidyalaya,Church Road,Colombo 02 |  |  | 950 | EI |  | 1 | 250000 | [6 empty] | 1 | [16 empty] | ZED
45 | MR | 2018/DCB/MR/COL/74 | Purchase of items and equipments required for WP /Co/ Clifton Girls School,Maligakanda,Colombo 10 | Maligakanda | 40 | 950 | EI |  | 1 | 250000 | [6 empty] | 1 | [16 empty] | ZED
46 | SS | 2018/DCB/SS/COL/75 | Balance work in Building of Central Young Muslim Association,Colombo Central | Kochchikade South | 30 | 950 | CD | 1 |  | 250000 |  | 249993.21 | 242711.85 | 3640.67 | 246352.54 | [15 empty] | 300 |  |  | DS | bar: B C
47 | SS | 2018/DCB/SS/COL/76 | Reconstruction of the building of the Muslim Dhamma School at Madrasathus Salam Church,Maligawththa | Maligawatta East | 26 | 950 | CD | 1 |  | 300000 |  | 299997.72 | 291259.92 | 4368.9 | 295628.82 | [18 empty] | DS | bar: B ii
48 | SS | 2018/DCB/SS/COL/77 | Reconstruction of washrooms,bathrooms at 41 watta,Muhamdiram Road |  |  | 950 | CD | 1 |  | 300000 | [6 empty] | 1 | [16 empty] | DS |  |  |  | නාමය සංශෝධනය විය යුතු බව දන්වා ඇත
49 | SS | 2018/DCB/SS/COL/78 | Concreting the balance from the house No 162/477 in Kibulaala,Madapitiya | Modara | 11 | 950 | RA | 1 |  | 300000 |  | 299989.77 | [21 empty] | DS | bar: B i
50 | SM | 2018/DCB/SM/COL/79 | Construction of Childrens Playground in Bloemandhal Housing Complex,Colombo 15 | Aluthmawatha | 14 | 950 | CD | 1 |  | 250000 | [6 empty] | 1 | [13 empty] | 400 |  |  | DS
51 | SM | 2018/DCB/SM/COL/80 | Concreting or Interlocking paving blocks in No.210,Aluthyonstreet,Colombo 12 |  |  | 950 | RA | 1 |  | 250000 | [6 empty] | 1 | [20 empty] | ක්‍රියාත්මක කළ නොහැකි
52 | SM | 2018/DCB/SM/COL/81 | Reconstruction of toilets system at No.53, Aluthyonstreet,Colombo 12 | Kochchikade South | 30 | 950 | CD | 1 |  | 250000 | [6 empty] | 1 | [13 empty] | 80 |  |  | DS
53 | SM | 2018/DCB/SM/COL/82 | Interlocking paving blocks in No.139, Central Road,Colombo 12 |  |  | 950 | RA | 1 |  | 250000 | [6 empty] | 1 | [20 empty] | ක්‍රියාත්මක කළ නොහැකි
54 | SM | 2018/DCB/SM/COL/83 | Renovation of buildings at Al-Ameen School, Maker Marikkar Mawatha,Colombo 03 | GalleFace | 33 | 950 | EI | 1 |  | 250000 | [6 empty] | 1 | [16 empty] | DE
| SM | 2018/DCB/SM/COL/85 | SUPPLY OF MALTI MEDIA PROJECT FOR YOUNG MUSLIM ASSOCIATION NO 53, WILSON STREET COLOMBO 12. | ALUTH MAWATHA | 14 | COLOMBO CENTRAL | SW |  | 1 | 150000 | [6 empty] | 1 | [16 empty] | DS
55 | SM | 2018/DCB/SM/COL/86 | Concreting or Interlocking paving blocks in No.120 watta,Maligawatta Place,Colombo 10 | Keththarama | 27 | 950 | RA | 1 |  | 250000 |  | 249994.97 | [18 empty] | 450 |  |  | DS | bar: B i
56 | SM | 2018/DCB/SM/COL/88 | Reconstruction of toilets system at No.120 watta,Sangamitta Mawatha,Colombo 13 | Msangasveediya | 21 | 950 | CD | 1 |  | 250000 | [6 empty] | 1 | [16 empty] | DS
57 | SM | 2018/DCB/SM/COL/89 | Providing water for the public toilets system at No.53 Watte, Pir Sibu Street,Colombo 12 | Aluthkade West | 29 | 950 | RW | 1 |  | 100000 | [6 empty] | 1 | [13 empty] | 67 |  |  | WB
| SM | 2018/DCB/SM/COL/90 | SUPPLY OF EQUIFMENTS TO GAMUNU BO SEWANA BARAKARA SAMITHIYA NO:B/1/3CENTRAL HOUSING SCHEEM MARADANA, COLOMBO 10 | MARADANA | 41 | COLOMBO CENTRAL | SW |  | 1 | 100000 | [6 empty] | 1 | [16 empty] | DS
58 | SM | 2018/DCB/SM/COL/91 | Concreting or Laying carpet at No. 132,Dimel watta,Grandpass Road,Colombo 14, | Grandpass |  | 950 | RA | 1 |  | 200000 | [6 empty] | 1 | [20 empty] | ක්‍රියාත්මක කළ නොහැකි
59 | RK | 2018/DCB/RK/COL/93 | Completed Partially completed work path at access road to the "Jayamanga Sevana" Housing Complex, Sirimavo Bandaranaike Mawatha,Colombo 14, - Second stage | Bloemendhal | 16 | 950 | RA | 1 |  | 1000000 |  | 999983.44 | 974560.14 | 12711.65 | 987271.79 | [15 empty] | 750 |  |  | DS | bar: B ii
60 | NL/TS | 2018/DCB/NL/TS/COL/94 | Development work of Sri Sarananda Buddhist Center,Jinthupitiya | Jinthupitiya | 20 | 950 | CD | 1 |  | 100000 |  | 99997.67 | 97085.13 | 1456.27 | 98541.4 | [15 empty] | 350 |  |  | DS | 129 Prajasanwardhana Samithiya | bar: B D
61 | NL/FM | 2018/DCB/NL/FM/COL/95 | Supplying photocopy machine for the Colombo 10,Sri Sangarajaya Central College belonging to the Colombo Divisional Secretary's Division |  |  | 950 | EI |  | 1 | 110000 | [6 empty] | 1 | [16 empty] | ZED
62 | NL/FM | 2018/DCB/NL/FM/COL/96 | Electrical Repair of No.05 Building at Vijayaba Vidyalaya | Grandpass North | 24 | 950 | EI | 1 |  | 100000 | 100000 |  | 97457.62 | 1271.19 | 98728.81 | [15 empty] | 695 |  |  | DE | bar: B ii
| NLMF | 2018/DCB/NLMF/COL/97 | Supplying of building materials for development work of multi purpose building kotahena paramananda dharma vidyalaya ,colombo 13 | kotahena |  |  | SW |  | 1 | 75000 | [6 empty] | 1 | [13 empty] | 400 |  |  | DS
| NLMF | 2018/DCB/NLMF/COL/98 | Supplying of building materials for constructions work of modara sri bodhisamudraramaya ,colombo 15 | modara | 11 |  | SW |  | 1 | 75000 | [6 empty] | 1 | [13 empty] | 520 |  |  | DS
| FM | 2018/DCB/NL/FM/COL/99 | SUPPLY OF SPORTS GOODS FOR SINHA SPORTS SOCIETY NO 358/1/1, ALUTH MAWATHA , COLOMBO 15. | ALUTH MAWATHA | 14 | COLOMBO NORTH | SW |  | 1 | 75000 | 74810 |  |  |  |  | 74810 | [17 empty] | DS | bar: B i
| FM | 2018/DCB/NL/FM/COL/100 | SUPPLY OF GOODS FOR NIRMANI KALA SANSADAYA COLOMBO 15. | ALUTH MAWATHA | 14 | COLOMBO NORTH | SW |  | 1 | 160000 | 160000 |  |  |  |  | 160000 | [17 empty] | DS | bar: B i
| NLMF | 2018/DCB/NLMF/COL/101 | Supplying of building materials for construction work of daham building siri saranankara temple ,520/125, bluemendal road, colombo 15 | bluemendal |  |  | SW |  | 1 | 75000 | [6 empty] | 1 | [13 empty] | 420 |  |  | DS
63 | NL/FM | 2018/DCB/NL/FM/COL/102 | Modernization of the front wall and the gate of Kotahena Central College,Colombo 13 (First Step) | Masangasveediya | 21 | 950 | EI | 1 |  | 700000 | [6 empty] | 1 | [20 empty] | ක්‍රියාත්මක කිරීමට නොහැකි බව දන්වා ඇත
| FM | 2018/DCB/NL/FM/COL/104 | BEAUTI CULTRE TRAINING PROGRAMME (FOUNDATION LEVEL)FOR SELF EMPLOYERS. | SEVERAL G.N.DIVISION INCLUDED |  | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 100000 | [6 empty] | 1 | [16 empty] | DS
64 | BG | 2018/DCB/BG/COL/105 | Constauction work in Sri Rahula Dhaham school building in Kalyani Nadi Viharaya,Madampitiya | Madampitiya | 12 | 950 | CD | 1 |  | 100000 |  | 99922.51 | 97012.15 | 1455.18 | 98467.33 | [18 empty] | DS | bar: B ii
| SS | 2018/DCB/SS/COL/106 | VOCATIONAL TRAINING PROGRAMME FOR SELF EMPLOYEMENT IN COLOMBO DIVISIONAL SECTRATARIAT | SEVERAL G.N.DIVISION INCLUDED |  | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 100000 | [6 empty] | 1 | [16 empty] | DS
| SS | 2018/DCB/SS/COL/107 | VOCATIONAL TRAINING PROGRAMME FOR SELF EMPLOYEMENT IN COLOMBO DIVISIONAL SECTRATARIAT | SEVERAL G.N.DIVISION INCLUDED |  | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 100000 | [6 empty] | 1 | [16 empty] | DS
| SS | 2018/DCB/SS/COL/108 | VOCATIONAL TRAINING PROGRAMME FOR SELF EMPLOYEMENT IN COLOMBO DIVISIONAL SECTRATARIAT | SEVERAL G.N.DIVISION INCLUDED |  | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 100000 | [6 empty] | 1 | [16 empty] | DS
| NLTM | 2018/DCB/NLTM/COL/109 | Supplying of building materials for constructions work of modara sri bodhisamudraramaya ,colombo 15 | madara | 11 |  | SW |  | 1 | 100000 | [6 empty] | 1 | [13 empty] | 380 |  |  | DS
65 | SM | 2018/DCB/SM/COL/110 | Installation of the main entrance at Mallikaramaya House scheme,Dematagoda,Colombo 09 | Maligawatta East | 26 | 950 | CD | 1 |  | 150000 | [6 empty] | 1 | [13 empty] | 250 |  |  | DS
| SM | 2018/DCB/SM/COL/111 | SUPPLY OF SPORT EQUIFMENT FOR UNITED SPORT SOCIETY,DHARMARAMA RD,DEMATAGODA COLOMBO 09. | DEMATAGODA |  | COLOMBO CENTRAL | SW |  | 1 | 100000 | 100000 |  |  |  |  | 100000 | [17 empty] | DS | bar: B i
66 | NL/FM | 2018/DCB/NL/FM/COL/112 | Repairs to toilets atNo.75,Central Road, Colombo 12 |  |  | 950 | CD | 1 |  | 150000 | [6 empty] | 1 | [20 empty] | ක්‍රියාත්මක කිරීමට නොහැකි බව දන්වා ඇත
67 | NL/FM | 2018/DCB/NL/FM/COL/113 | Defense net for Nawagampura Community Hall | Nawagampura | 25 | 950 | CD | 1 |  | 150000 |  | 149996.6 | [21 empty] | DS | bar: B i
68 | NL/FM | 2018/DCB/NL/FM/COL/114 | Modernization of the Solar equipment fixing system for 10 named schools |  |  | 950 | EI |  | 1 | 4000000 | [6 empty] | 1 | [16 empty] | ZED
| NLFM | 2018/DCB/NLFM/COL/115 | Suplly of plastic chairs for registed buddhist dhamma school | all gn |  |  | SW |  | 1 | 500000 | [6 empty] | 1 | [13 empty] | 280 |  |  | DS
| NLFM | 2018/DCB/NLFM/COL/116 | Suplly of plastic chairs for registed islamic mosques | all gn |  |  | SW |  | 1 | 750000 | [6 empty] | 1 | [13 empty] | 440 |  |  | DS
| NLFM | 2018/DCB/NLFM/COL/117 | Suplly of plastic chairs for registed hindu kovil | all gn |  |  | SW |  | 1 | 150000 | [6 empty] | 1 | [13 empty] | 260 |  |  | DS
| NLFM | 2018/DCB/NLFM/COL/118 | Suplly of plastic chairs for registed cathalic churchs | all gn |  |  | SW |  | 1 | 100000 | [6 empty] | 1 | [13 empty] | 330 |  |  | DS
| NLFM | 2018/DCB/NLFM/COL/119 | Suplly of band instruments for registed preschools | all gn |  |  | SW |  | 1 | 800000 | [6 empty] | 1 | [13 empty] | 470 |  |  | DS
| FM | 2018/DCB/NL/FM/COL/120 | SUPPLY OF GOODS FOR PRAJA SANWARDHANA SAMITHIYA NO:128,JINTHUPITIYA. | JINTHUPITIYA | 20 | COLOMBO NORTH | SW |  | 1 | 350000 | [6 empty] | 1 | [13 empty] | 500 |  |  | DS
| FM | 2018/DCB/NL/FM/COL/121 | SUPPLY OF GOODS FOR YOUNG SOCIETY KOCHCHIKADE NORTH | KOTAHENA | 19 | COLOMBO CENTRAL | SW |  | 1 | 350000 | [6 empty] | 1 | [16 empty] | DS
69 | AD | 2018/DCB/AD/COL/122 | Supplying equipment necessary for a smart class room for Kotahena Kumara Vidyalaya |  |  | 950 | EI |  | 1 | 250000 | [6 empty] | 1 | [16 empty] | ZED
70 | AD | 2018/DCB/AD/COL/123 | Constuction work in Subodharama Viharaya building,Malgawatte,Colombo 10 | Maligawatta West | 29 | 950 | CD | 1 |  | 230000 |  | 229997.49 | 223298.53 | 3349.48 | 226648.01 | [18 empty] | DS | Sri Subodharama Viharastha Dayakasabhawa | bar: B C
| IW | 2018/DCB/IW/COL/125 | SUPPLY OF GOODS & EQUIPMENTS FOR NOMINATED SOCIETY IN DIVISIONAL SECRETARIEAT COLOMBO. | SEVERAL G.N.DIVISION INCLUDE |  | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 200000 | [6 empty] | 1 | [16 empty] | DS
71 | IW | 2018/DCB/IW/COL/126 | Reconstruction of toilets at 238,226,232,323 watta,Lunapokuna,Alawathawatta, Colombo 15 |  |  | 950 | CD | 1 |  | 300000 | [6 empty] | 1 | [16 empty] | DS |  |  |  | මුදල ප්‍රමාණවත් නොවන බව දන්වා ඇත
72 | SM | 2018/DCB/SM/COL/127 | Reconstruction of public toilets of No. 98,Kiwi Road,Colombo 02 | Hunupitiya | 35 | 950 | CD | 1 |  | 450000 |  | 199999.55 | 194174.33 | 2912.61 | 197086.94 | [18 empty] | DS | bar: B ii
73 | RW | 2018/DCB/RW/COL/129 | Concrete the entry road at No.42,St. Benedict Mawatha,Colombo 13.(Bloemandhal) |  |  | 950 | RA | 1 |  | 100000 | [6 empty] | 1 | [16 empty] | DS |  |  |  | මුදල ප්‍රමාණවත් නොවන බව දන්වා ඇත
| RW | 2018/DCB/RW/COL/130 | SUPPLY OF PLASTIC CHAIRS FOR ST.LUSIA CHURCH KOTAHENA, COLOMBO 13. | KOTAHENA |  | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 100000 | 99840 | [22 empty] | DS | bar: B i
74 | RW | 2018/DCB/RW/COL/131 | Reconstruction of Bodhimandalarama Temple,Cyril C. Perera Mawatha,Colombo 13. |  |  | 950 | CD | 1 |  | 150000 | [6 empty] | 1 | [16 empty] | DS
| DG | 2018/DCB/DG/COL/132 | SUPPLY OF GOODS & EQIPMENT FOR WELFARE SOCIETY& ELDER SOCIETY IN DIVISIONAL SECRETARIEAT COLOMBO. | MATTAKKULIYA | 10 | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 100000 | 100000 |  |  |  |  | 100000 | [17 empty] | DS | bar: B i
75 | RW | 2018/DCB/RW/COL/133 | Repairing of water well at 70 watta,Maligawatte Lane | Maligawatta East | 39 | 950 | SW | 1 |  | 200000 |  | 199967.1 | 194142.82 | 2912.14 | 197054.96 | [15 empty] | 270 |  |  | DS | bar: B ii
76 | RW | 2018/DCB/RW/COL/134 | Repair of drainage System at No.28 watta,Akkara Lane,Colombo 12 |  |  | 950 | CD | 1 |  | 200000 | [6 empty] | 1 | [20 empty] | ක්‍රියාත්මක කිරීමට නොහැකි බව දන්වා ඇත
77 | RW | 2018/DCB/RW/COL/135 | Interlocking paving blocks in front Welfare Building,Crow Island,Mattakkuliya | Mattakkuliya | 10 | 950 | RA | 1 |  | 250000 |  | 249971.06 | 242690.36 | 3640.35 | 246330.71 | [18 empty] | DS | bar: B C
78 | NL/FM | 2018/DCB/NL/FM/COL/136 | Interlocking paving blocks in No. 265/7, Masjith Muniwara Jumma Church Dhamma School,Sri Saddhara Mawatha,Colombo 10 | Maligawatta East | 39 | 950 | RA | 1 |  | 350000 |  | 349989.93 | [18 empty] | 450 |  |  | DS | bar: B i
| MF | 2018/DCB/NL/MF/COL/138 | SUPPLY OF PHOTOCOPY MACHINE FOR KALYANI GANGARAMAYA,MATTAKKULIYA ,COLOMBO 15. | MATTAKKULIYA | 10 | COLOMBO NORTH | SW |  | 1 | 50000 | [6 empty] | 1 | [16 empty] | DS
| MF | 2018/DCB/NL/MF/COL/139 | SUPPLY OF PLASTIC CHAIRS FOR HARBOUR VIEW PARK RESIDENT SOCIETY ,WISWIKE RD CROW ISLAND,MATTAKKULIYA,COLOMBO 15 | MATTAKKULIYA | 10 | COLOMBO NORTH | SW |  | 1 | 50000 | 49761 | [22 empty] | DS | bar: B i
79 | WR | 2018/DCB/WR/COL/140 | Construction of Dhaham school building at Sri Paramananda Dharma school,Kotahena | Kotahena East | 17 | 950 | CD | 1 |  | 200000 |  | 199999.67 | 194174.44 | 2912.61 | 197087.06 | [18 empty] | DS | 129 Prajasanwardhana Samithiya | bar: B D
80 | AD | 2018/DCB/AD/COL/141 | Supplying photocopy machine for St.James College,Modera,Colombo 15 |  |  | 950 | EI |  | 1 | 220000 | [6 empty] | 1 | [16 empty] | ZED
81 | AD | 2018/DCB/AD/COL/142 | Supplying Imaging Equipment for the Cathidral (Male) College,Colombo 13 |  |  | 950 | EI |  | 1 | 100000 | [6 empty] | 1 | [16 empty] | ZED
| SM | 2018/DCB/SM/COL/143 | SUPPLY OF GOODS &EQUIPMENTS SRI WAYSHAKHALOKA NALAGAMWEEDIYA COLOMBO 14 | MAHAWATTA | 13 | COLOMBO CENTRAL | SW |  | 1 | 200000 | 199580 | [22 empty] | DS | bar: B i
| SM | 2018/DCB/SM/COL/145 | Supplying of building materials for development work of bilal jumma masgithaya, no 151/1 ,maligawatta place,maligawatta,colombo 10 | khethtarama |  |  | SW |  | 1 | 750000 | [6 empty] | 1 | [13 empty] | 610 |  |  | DS
| HS | 2018/DCB/HS/COL/146 | SUPPLY OF EQUIPMENTS FOR JINARATHANA TRAINING VIDYALAYA | SLAVE ISLAND | 34 | COLOMBO CENTRAL | SW |  | 1 | 500000 | [6 empty] | 1 | [16 empty] | DS
82 | MG | 2018/DCB/MG/COL/147 | Supply electricity and water to Community Hall at No.1/2P/4,Kadirana watte,Mattakkuliya,Colombo 15 | Mattakkuliya | 10 | 950 | CD | 1 |  | 60000 | [6 empty] | 1 | [13 empty] | 275 |  |  | DS
83 | MG | 2018/DCB/MG/COL/148 | Supply electricity,water and ceiling of library at No. 1/3 F,Kadirana watte,Mattakkuliya,Colombo 15 |  |  | 950 | CD | 1 |  | 150000 | [6 empty] | 1 | [16 empty] | DS |  |  |  | මුදල ප්‍රමාණවත් නොවන බව දන්වා ඇත
84 | MG | 2018/DCB/MG/COL/149 | Concreting the road section No. RFK 1 to 70 at Mattakkuliya, Kadiranawatta, Colombo 15 | Mattakkuliya | 10 | 950 | RA | 1 |  | 500000 |  | 499982.58 | [21 empty] | DS | bar: B i
85 | MG | 2018/DCB/MG/COL/150 | Reconstruction of Community Hall and supplying electricity and water at Rawathawatta,Mattakkuliya,Colombo 15 | Mattakkuliya | 10 | 950 | CD | 1 |  | 250000 | [6 empty] | 1 | [16 empty] | DS
86 | MG | 2018/DCB/MG/COL/151 | Interlocking paving blocks in No. 68 to 71,Kadiranawatta Ekamuthupura,Mattakkuliya,Colombo 15 | Mattakkuliya | 10 | 950 | RA | 1 |  | 500000 |  | 399441.73 | [21 empty] | DS | bar: B i
| MG | 2018/DCB/MG/COL/152 | SUPPLY OF HUT & CHAIRS FOR REGISTERED SPCIETY IN COLOMBO DIVISIONAL SECRETARIAT. | SEVERAL G.N.DIVISION INCLUDE |  | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 2000000 | [6 empty] | 1 | [16 empty] | DS
| MG | 2018/DCB/MG/COL/153 | SUPPLY OF SPORT GOODS & EQUIPMENTS FOR REGISTERED SPORTS SOCIETY IN COLOMBO DIVISIONAL SECRETARIAT. | SEVERAL G.N.DIVISION INCLUDE |  | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 2000000 | [6 empty] | 1 | [16 empty] | DS
87 | SF | 2018/DCB/NL/SF/COL/155 | Renovation of the skeletal system and establishment of a water tank,depressed walls of St John's temple in Modara | Aluthmawatha | 14 | 950 | CD | 1 |  | 250000 |  | 249999.18 | [21 empty] | DS | bar: B i
| Hon.sarath fonseka | 2018/DCB/NLSF/COL/156 | Supplying of building materials for construction work of lankaramaya, colombo 14 | nawagampura | 25 |  | SW |  | 1 | 75000 | [6 empty] | 1 | [13 empty] | 560 |  |  | DS
88 | SF | 2018/DCB/NL/SF/COL/157 | Reconstruction of public toilets at No.90 watta,Modara | Aluthmawatha | 14 | 950 | CD | 1 |  | 370000 |  | 369999.5 | [21 empty] | DS | bar: B i
89 | SF | 2018/DCB/NL/SF/COL/158 | Repair of drainage System at No.27 watta,Madampitiya Road,Modara | Modara | 11 | 950 | CD | 1 |  | 1000000 | [6 empty] | 1 | [16 empty] | CMC
| MF | 2018/DCB/MF/(NL)/COL/159 | SUPPLY OF EQIPMENT TO FSHERIES AND COMMON VOLUNTEER ORGANIZATION , NO 358 1/1, ALUTH MAWATHER ,COL15 | ALUTH MAWATHA | 14 | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 450000 | 449984 | [22 empty] | DS | bar: B i
| MS | 2018/DCB/NL/MS/COL/160 | SUPPLY OF CHAIRS FOR VIVEKANANDA SOCIETY NO:34 VIVEKANANDA HILL | JINTHUPITIYA | 20 |  | SW |  | 1 | 500000 | 499356 |  |  |  |  | 499356 | [17 empty] | DS | bar: B i
| MS | 2018/DCB/NL/MS/COL/161 | SUPPLY OF HUT & CHAIRS FOR SITHTHIVINAYARGAR KOVIL NO:99 JINTHUPITIYA | JINTHUPITIYA | 20 | COLOMBO CENTRAL COLOMBO NORTH | SW |  | 1 | 500000 | 499640 | [22 empty] | DS | bar: B i
90 | MS | 2018/DCB/NL/MS/COL/162 | Construction of the Access road at No.172,Wolfendal Street |  |  | 950 | RA | 1 |  | 250000 | [6 empty] | 1 | [16 empty] | DS
91 | MS | 2018/DCB/NL/MS/COL/163 | Repairs to the drainage system/drainage system of the F.R.Samarimuththu Memorial Hall at No.98,Chekku Street |  |  | 950 | RA | 1 |  | 300000 | [6 empty] | 1 | [16 empty] | CMC
92 | MS | 2018/DCB/NL/MS/COL/164 | Reconstruction of the building of All Island Bharatha Society at No.36,Brass Pounder Mw. |  |  | 950 | RA | 1 |  | 300000 | [6 empty] | 1 | [16 empty] | DS
93 | MS | 2018/DCB/NL/MS/COL/165 | Construction of 3 storied building at Maligawatta International Buddhist Research Library |  |  | 950 | RA | 1 |  | 300000 | [6 empty] | 1 | [16 empty] | DS
94 | SF | 2018/DCB/NL/SF/COL/166 | Installation of heaters and fans and The ceiling of the Siri Cooray Father's Church hall of the St.Jone Church |  |  | 950 | CD | 1 |  | 1000000 | [6 empty] | 1 | [16 empty] | DS
95 | RW | 2018/DCB/RW/COL/167 | Repairs to toilets at No.155 watta,Mohideen masjith Road,Panchikawatta |  |  | 950 | CD | 1 |  | 200000 | [6 empty] | 1 | [16 empty] | DS
96 | MR | 2018/DCB/MR/COL/168 | Development of 204 watta at Maligakanda,Dematagoda, Colombo 14 |  |  | 950 | CD | 1 |  | 100000 | [6 empty] | 1 | [16 empty] | DS
97 | MR | 2018/DCB/MR/COL/169 | Development of Public toilet and bathroom with plastic door at Prince Road,Colombo 14 |  |  | 950 | CD | 1 |  | 50000 | [6 empty] | 1 | [16 empty] | DS
98 | RK | 2018/DCB/RK/COL/171 | Rehabilitation of drainage system at 04 Lane,Crow Island,Mattakkuliya |  |  | 950 | CD | 1 |  | 1000000 | [6 empty] | 1 | [16 empty] | DS
Total | [7 empty] | 68 | 56 | 41570000 | 4897461 | 8185562.65 | 7081563.91 | 99807.09 | 7181371.07 | 1233656 | 78 | 21 | 16 | 1 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19275 | 0
** Physical progress
[7 empty] | Description for rating | [10 empty] | B ii: Rates; B C: Percentage Ranges | * Projects should be categorized for following sectors
[7 empty] | For Construction Project | [5 empty] | For Puchasing Projects | [13 empty] | Under DCB Programme |  |  |  | Under Rural Infrastructure Development Programme (Special Projects) and 20 Millon
[7 empty] | Estimate is being / to be prepared and initial works started | [5 empty] | Requirements Not Called |  |  |  |  | B ii: A; B C: (0 - 5)% | WS- Rural Water Supply |  |  |  | WS - Rural Water Supply
[7 empty] | B1 | Estimates approved / Bid documents prepared, |  |  |  |  | B1 | Requirements Called |  |  |  | B ii: B; B C: (6 - 25)% | EL- Rural Electricity |  |  |  | RA - Rural Access
[7 empty] | B2 | Quotation / Bid called |  |  |  |  | B2 | Requirements Received | [12 empty] | RA- Rural Access |  |  |  | EI - Economic Infrastructure
[7 empty] | B3 | Quotation / Bid Received |  |  |  |  | B3 | Qutation called | [12 empty] | EI- Economic Infrastructure |  |  |  | RE - Rural Economy
[7 empty] | B4 | Contract Awarded. (25% completed) |  |  |  |  | B4 | Estimated prepared | [12 empty] | RW- Rural Welffare |  |  |  | SW- Social Welfare
[27 empty] | CD- Community Development |  |  |  | EL - Rural Electricity
[7 empty] | Constructions : Started construction works , (40% completed) | [5 empty] | Placed orders for goods / instruments |  |  |  |  | B ii: C; B C: (26 - 40)% | MI- Minor Irrigation |  |  |  | PW - Public Welfare
[27 empty] | SW- Social Welfare |  |  |  | OI - Other Infrastructure
[7 empty] | Constructions : 60% Completed | [10 empty] | B ii: D; B C: (41 - 60)% | Under Sukitha purawara
SC -Sanitary and common facilities ( සනීපාරක්ෂක හා පොදු පහසුකම්)
[7 empty] | Constructions : 80% Completed | [5 empty] | Received goods / instruments as per the order |  |  |  |  | B ii: E; B C: (61 - 80)% | RD - Sanitary and common facilities Road and Derange Development (මාර්ග හා කාණු පද්ධති සංවර්ධනය)
MC -Maternity and Child Clinic ( මාතෘ හා ළමා සායන)
[7 empty] | Constructions : 99% Completed | [5 empty] | Completed lists of goods to be given to beneficiaries |  |  |  |  | B ii: F; B C: (81 - 99)% | SS - School and Sports (පාසල් හා ක්‍රීඩා සංවර්ධනය)
CH - Community Hall and Sewapiyasa (ප්‍රජා ශාලා හා සේවා පියස ගොඩනැගිලි සංවර්ධනය)
[7 empty] | Constructions : 100% Complete | [5 empty] | Issued goods and instruments to identified institutions/ CBOs |  |  |  |  | B ii: G; B C: 100% | RP - Religious center Developments (ආගමික මධ්‍යස්ථාන සංවර්ධනය)

## Summary
Decentralized Capital Budget Programme -2018 - Colombo District
Physical and Financial Progress JULY 2018
| Division | colombo
| Vote | 950
S.No. | Sector | No of Total Projects | Type of Project |  | Allocation (Rs.) | Total Estimate Cost (Rs.) |  | Amount of Released Allocation (Rs) |  |  | Agreement Cost (Rs) | Physical Progress (c) | [9 empty] | Financial Progress |  |  |  | No of Beneficiaries
[12 empty] | A | B |  |  |  | C | D | E | F | G | Expenditure (Work Done)(Rs) | Vat (Rs) | Admin Cost (Rs) | Total Expenditure (Rs)
|  |  | Construction | Puchersing |  | With VAT | Without VAT | Without Adm (Rs) | Admin (1.5%) (Rs) | Total (Rs) |  |  | i | ii | iii | iv
1 | WS
2 | EL
3 | RA | 30 | 30 |  | 10835000 |  | 6569893.31 | 4300062.71 | 62594.18 | 4362656.89 |  | 13 | 7 | 3 |  |  | 6 |  |  |  | 1 | 485435.99 |  | 7281.53 | 492717.52 | 4686
4 | EI | 26 | 13 | 13 | 10865000 | 2365000 | 250000 | 2547591.34 | 33704.32 | 2581295.68 |  | 18 |  | 7 |  |  | 1 | [8 empty] | 5957
5 | RW | 2 | 2 |  | 175000 |  | 74227.16 | 72065.22 | 1080.97 | 73146.19 |  | 1 |  |  | 1 | [10 empty] | 222
6 | CD | 38 | 38 |  | 11230000 |  | 4069851 | 2718307.18 | 40774.56 | 2758081.78 |  | 22 | 4 | 6 | 1 |  | 3 | 2 | [7 empty] | 3675
7 | MI
8 | SW | 45 | 2 | 43 | 15000000 | 2532461 | 199967.1 | 194142.82 | 2912.14 | 197054.96 | 1233656 | 33 | 11 | 1 | [11 empty] | 7370
9 | SS
10 | CP
11 | LD
RE
Total |  | 141 | 85 | 56 | 48105000 | 4897461 | 11163938.57 | 9832169.27 | 141066.17 | 9972235.5 | 1233656 | 87 | 22 | 17 | 2 | 0 | 10 | 2 | 0 | 0 | 1 | 485435.99 | 0 | 7281.53 | 492717.52 | 21910
* Projects should be categorized for following sectors
| WS- Rural Water Supply | [5 empty] | SS- Social Services
| EL- Rural Electricity | [5 empty] | CP- Community Protection
| RA- Rural Access | [5 empty] | LD - Livelihood Development
| EI- Economic Infrastructure | [5 empty] | RE- Rural Economy
RW- Rural Welffare
CD- Community Development
MI- Minor Irrigation
SW- Social Welfare

## Sheet1
Decentralized Capital Budget Programme - 2018 - Colombo District
අනු අංක | ක්‍රියාත්මක බලධාරී ආයතනය | ව්‍යාපෘති සංඛ්‍යාව | වෙන් කළ මුදල (රු.) | සමස්ත ඇස්තමේන්තුව (රු.) | නිදහස් කල ප්‍රතිපාදන (රු.) | වියදම (රු.) | භෞතික ප්‍රගතිය
[7 empty] | A | B | C | D | E
1 | ප්‍රාදේශීය ලේකම් (ඉදිකිරීම්) | 58 | 18310000 | 10768686.15 | 7391939.82 | 492717.52 | 24 | 10 | 12 | 11 | 1 |  | 58
2 | ප්‍රාදේශීය ලේකම් (මිල දී ගැනීම්) | 43 | 14680000 | 2532461 |  |  | 32 | 11 |  |  |  | 43
3 | කලාප අධ්‍යාපන කාර්යාලය (මිල දී ගැනීම්) | 13 | 6330000 |  |  |  | 13
4 | ප්‍රාදේශීය ඉංජිනේරු | 12 | 3835000 | 2615000 | 2581295.68 |  | 4 | 7 | 1
5 | කොළඹ නගර සභාව | 3 | 1500000 | 145252.42 |  |  | 2 | 1
6 | ජල සම්පාදන හා ජලාප්‍රවාහන මණ්ඩලය | 1 | 100000 |  |  |  | 1
7 | ගැටළු | 11 | 3350000 |  |  |  | 11
එකතුව |  | 141 | 48105000 | 16061399.57 |  |  | 87 | 29 | 13 | 11 | 1
| A - ඇස්තමේන්තු සකස්කරීමට ඇති |  |  | B - ඇස්තාමේන්තු සකස්කර ප්‍රතිපාදන ගෙන්වීමට දි.ලේ යොමුකර ඇති
| C - ප්‍රතිපාදන ලබා ඉදිරි කටයුතු කිරීම |  |  | D -වැඩ ආරම්භකර ඇති
| E - වැඩ අවසන් | [8 empty] | 129