## Detail
Colombo District
Religion Center Development Programe
Physical and Financial Progress of the Month of 6th of July 2018
| Division | Colombo
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
SN | Code of MP | Project No | Project Name | G.N. Division |  | Electorate Division | Sector | Type of Project |  | Allocation (Rs.) | Total Estimate Cost (Rs.) |  | Amount of Released Allocation (Rs) |  |  | Agreement Cost (Rs) | Physical Progress (c) | [9 empty] | Financial Progress |  |  |  | No of Beneficiaries | Measurement |  | Implementing Agency | CBO/ Contractor | Starting Date | End Date | Remarks
[17 empty] | A | B | [8 empty] | Expenditure (Work Done)(Rs) | Tax (Rs) (Vat , NBT) | Admin Cost (1.5%,0.5%) (Rs) | Total Expenditure (Rs)
|  |  |  | Name | No |  |  | Construction | Puchasing |  | TAX (Rs) (VAT , NBT | Without TAX (Rs) | Without Adm (Rs) | Admin (1.5%/0.5%) (Rs) | Total (Rs) |  |  | i | ii | iii | iv | C | D | E | F | G | [5 empty] | Key performance indicator | Value of mesurment
1 |  | 2018/Religious/2018/Col/01 | complete balance work Daham pasal building at sri Rahula daham pasala,kelani nadee viharaya,Fregusion Rd.,Colombo 15. | Madampitiya | 12 | Colombo north | CD | 1 |  | 500000 | [6 empty] | 1
2 |  | 2018/Religious/2018/Col/01 | Renovation of st.Antony church Kochchikade | Kochchikade North | 19 | Colombo north | CD | 1 |  | 500,00.00 | [6 empty] | 1
3
Total
** Physical progress
[7 empty] | Description for rating | [10 empty] | B ii: Rates; B C: Percentage Ranges | * Projects should be categorized for following sectors
[7 empty] | For Construction Project | [5 empty] | For Puchasing Projects | [13 empty] | Under DCB Programme |  |  |  | Under Rural Infrastructure Development Programme (Special Projects) and 20 Millon
[7 empty] | Estimate is being / to be prepared and initial works started | [5 empty] | Requirements Not Called |  |  |  |  | B ii: A; B C: (0 - 5)% | WS- Rural Water Supply |  |  |  | WS - Rural Water Supply
[7 empty] | B1 | Estimates approved / Bid documents prepared, |  |  |  |  | B1 | Requirements Called |  |  |  | B ii: B; B C: (6 - 25)% | EL- Rural Electricity |  |  |  | RA - Rural Access
[7 empty] | B2 | Quotation / Bid called |  |  |  |  | B2 | Requirements Received | [12 empty] | RA- Rural Access |  |  |  | EI - Economic Infrastructure
[7 empty] | B3 | Quotation / Bid Received |  |  |  |  | B3 | Qutation called | [12 empty] | EI- Economic Infrastructure |  |  |  | RE - Rural Economy
[7 empty] | B4 | Contract Awarded. (25% completed) |  |  |  |  | B4 | Estimated prepared | [12 empty] | RW- Rural Welffare |  |  |  | SW- Social Welfare
[27 empty] | CD- Community Development |  |  |  | EL - Rural Electricity
[7 empty] | Constructions : Started construction works , (40% completed) | [5 empty] | Placed orders for goods / instruments |  |  |  |  | B ii: C; B C: (26 - 40)% | MI- Minor Irrigation |  |  |  | PW - Public Welfare
[27 empty] | SW- Social Welfare |  |  |  | OI - Other Infrastructure
[7 empty] | Constructions : 60% Completed | [10 empty] | B ii: D; B C: (41 - 60)% | Under Sukitha purawara
SC -Sanitary and common facilities ( සනීපාරක්ෂක හා පොදු පහසුකම්)
[7 empty] | Constructions : 80% Completed | [5 empty] | Received goods / instruments as per the order |  |  |  |  | B ii: E; B C: (61 - 80)% | RD - Sanitary and common facilities Road and Derange Development (මාර්ග හා කාණු පද්ධති සංවර්ධනය)
MC -Maternity and Child Clinic ( මාතෘ හා ළමා සායන)
[7 empty] | Constructions : 99% Completed | [5 empty] | Completed lists of goods to be given to beneficiaries |  |  |  |  | B ii: F; B C: (81 - 99)% | SS - School and Sports (පාසල් හා ක්‍රීඩා සංවර්ධනය)
CH - Community Hall and Sewapiyasa (ප්‍රජා ශාලා හා සේවා පියස ගොඩනැගිලි සංවර්ධනය)
[7 empty] | Constructions : 100% Complete | [5 empty] | Issued goods and instruments to identified institutions/ CBOs |  |  |  |  | B ii: G; B C: 100% | RP - Religious center Developments (ආගමික මධ්‍යස්ථාන සංවර්ධනය)
Constructions: B - 1 = Estimates approved / Bid documents prepared, B - 2 = Quotation / Bid called B - 3 = Quotation / Bid Received B - 4 = Contract Awarded. (25% completed)

## Summary
Religion Center Development Programe
Physical and Financial Progress of the Month of 6th of July 2018
| Division | Colombo
S.No. | Sector | No of Total Projects | Type of Project |  | Allocation (Rs.) | Total Estimate Cost (Rs.) |  | Amount of Released Allocation (Rs) |  |  | Agreement Cost (Rs) | Physical Progress (c) | [9 empty] | Financial Progress |  |  |  | No of Beneficiaries
[12 empty] | A | B |  |  |  | C | D | E | F | G | Expenditure (Work Done)(Rs) | Vat (Rs) | Admin Cost (Rs) | Total Expenditure (Rs)
|  |  | Construction | Puchersing |  | With VAT | Without VAT | Without Adm (Rs) | Admin (1.5%) (Rs) | Total (Rs) |  |  | i | ii | iii | iv
1 | WS
2 | EL
3 | RA
4 | EI
5 | RW
6 | CD | 2 | 2 | 0 | 1000000 | [6 empty] | 2
7 | MI
8 | SW
9 | SS
10 | CP
11 | LD
RE
Total
* Projects should be categorized for following sectors
| WS- Rural Water Supply | [5 empty] | SS- Social Services
| EL- Rural Electricity | [5 empty] | CP- Community Protection
| RA- Rural Access | [5 empty] | LD - Livelihood Development
| EI- Economic Infrastructure | [5 empty] | RE- Rural Economy
RW- Rural Welffare
CD- Community Development
MI- Minor Irrigation
SW- Social Welfare

## Sheet1
Religion Center Development Programe - 2018 - Colombo District
අනු අංක | ක්‍රියාත්මක බලධාරී ආයතනය | ව්‍යාපෘති සංඛ්‍යාව | වෙන් කළ මුදල (රු.) | සමස්ත ඇස්තමේන්තුව (රු.) | නිදහස් කල ප්‍රතිපාදන (රු.) | වියදම (රු.) | භෞතික ප්‍රගතිය
[7 empty] | A | B | C | D | E
1
එකතුව |  | 0 | 0 | 0
| A - ඇස්තමේන්තු සකස්කරීමට ඇති |  |  | B - ඇස්තාමේන්තු සකස්කර ප්‍රතිපාදන ගෙන්වීමට දි.ලේ යොමුකර ඇති
| C - ප්‍රතිපාදන ලබා ඉදිරි කටයුතු කිරීම |  |  | D -වැඩ ආරම්භකර ඇති
| E - වැඩ අවසන් | [8 empty] | 0