## Detail
Colombo District
[7 empty] | Sukitha Purawara |  |  | Programme
Physical and Financial Progress of the Month of JULY- 2018
| Division | COLOMBO 950
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
SN | Code of MP | Project No | Project Name | G.N. Division |  | Electorate Division | Sector | Type of Project |  | Allocation (Rs.) | Total Estimate Cost (Rs.) |  | Amount of Released Allocation (Rs) |  |  | Agreement Cost (Rs) | Physical Progress (c) | [9 empty] | Financial Progress |  |  |  | No of Beneficiaries | Measurement |  | Implementing Agency | CBO/ Contractor | Starting Date | End Date | Remarks
[17 empty] | A | B |  |  |  | C | D | E | F | G | Expenditure (Work Done)(Rs) | Tax (Rs) (Vat , NBT) | Admin Cost (1.5%,0.5%) (Rs) | Total Expenditure (Rs)
|  |  |  | Name | No |  |  | Construction | Puchasing |  | TAX (Rs) (VAT , NBT | Without TAX (Rs) | Without Adm (Rs) | Admin (1.5%/0.5%) (Rs) | Total (Rs) |  |  | i | ii | iii | iv | [10 empty] | Key performance indicator | Value of mesurment
1 |  | SUK/COL/2018/01 | Drainage system and drainage drains at 134/142 up to 144 houses (750 beneficiary families) | Grandpass South | 23 | C.colombo | RD | 1 |  | 1500000 | [6 empty] | 1 | [13 empty] | 750 |  |  | DS |  |  |  | Nomination Amendments
2 |  | SUK/COL/2018/02 | Construction of Drainage System and Drainage at 134/170 up to 134/281 houses from Stespura (1000 beneficiary families) | Grandpass South | 23 | C.colombo | RD | 1 |  | 1500000 | [6 empty] | 1 | [13 empty] | 1000 |  |  | DS |  |  |  | To be Cancel
3 |  | SUK/COL/2018/03 | Construction of toilets System In front of the house 0f Stespura Second stage at 134/2A (800 beneficiary families) | Grandpass South | 23 | C.colombo | SC | 1 |  | 1500000 | [6 empty] | 1 | [13 empty] | 800 |  |  | CMC
4 |  | SUK/COL/2018/04 | Construction of toilet system infront of 134/70 (850 beneficiary families) | Grandpass South | 23 | C.colombo | SC | 1 |  | 1500000 | [6 empty] | 1 | [13 empty] | 850 |  |  | DS |  |  |  | Nomination Amendments
5 |  | SUK/COL/2018/05 | Construction of toilet system at senehehamige waththa,Grandpass,Colombo 14.( 950 beneficiary families) | Grandpass South | 23 | C.colombo | SC | 1 |  | 1500000 | [6 empty] | 1 | [13 empty] | 950 |  |  | DS |  |  |  | Nomination Amendments
6 |  | SUK/COL/2018/06 | Built a pump house and Installing two motors at the Kaththarama apartment building ( 1000 beneficiary families) | Grandpass South | 23 | C.colombo | SC | 1 |  | 500000 | [6 empty] | 1 | [13 empty] | 1000 |  |  | DS |  |  |  | Nomination Amendments
7 |  | SUK/COL/2018/07 | Rehabilitation of Staspura children's playground ( 1000 beneficiary families) | Grandpass South | 23 | C.colombo | SS | 1 |  | 2000000 | [6 empty] | 1 | [13 empty] | 1500 |  |  | DS
8 |  | SUK/COL/2018/08 | Drain drains,765/175 up to 325 A to 2 houses from Bodhirajaramaya Dutugemunu Lane ( 1000 beneficiary families) | Grandpass South | 23 | C.colombo | RD | 1 |  | 1500000 | [6 empty] | 1 | [13 empty] | 1000 |  |  | DS |  |  |  | Nomination Amendments
9 |  | SUK/COL/2018/09 | Drainage system and drainage drains at 765/327 to 342 houses from Bodhirajarama Dutugemunu lane (750 beneficiary families) | Grandpass South | 23 | C.colombo | RD | 1 |  | 1500000 | [6 empty] | 1 | [13 empty] | 750 |  |  | DS |  |  |  | Nomination Amendments
Total
8600
** Physical progress
[7 empty] | Description for rating | [11 empty] | Rates |  |  | Percentage Ranges |  |  |  |  | * Projects should be categorized for following sectors
[7 empty] | For Construction Project | [5 empty] | For Puchasing Projects | [13 empty] | Under DCB Programme |  |  |  | Under Rural Infrastructure Development Programme (Special Projects) and 20 Millon
[7 empty] | Estimate is being / to be prepared and initial works started | [5 empty] | Requirements Not Called | [5 empty] | A |  |  | (0 - 5)% |  |  |  |  | WS- Rural Water Supply |  |  |  | WS - Rural Water Supply
[7 empty] | B1 | Estimates approved / Bid documents prepared, |  |  |  |  | B1 | Requirements Called |  |  |  |  | B |  |  | (6 - 25)% |  |  |  |  | EL- Rural Electricity |  |  |  | RA - Rural Access
[7 empty] | B2 | Quotation / Bid called |  |  |  |  | B2 | Requirements Received | [12 empty] | RA- Rural Access |  |  |  | EI - Economic Infrastructure
[7 empty] | B3 | Quotation / Bid Received |  |  |  |  | B3 | Qutation called | [12 empty] | EI- Economic Infrastructure |  |  |  | RE - Rural Economy
[7 empty] | B4 | Contract Awarded. (25% completed) |  |  |  |  | B4 | Estimated prepared | [12 empty] | RW- Rural Welffare |  |  |  | SW- Social Welfare
[27 empty] | CD- Community Development |  |  |  | EL - Rural Electricity
[7 empty] | Constructions : Started construction works , (40% completed) | [5 empty] | Placed orders for goods / instruments | [5 empty] | C |  |  | (26 - 40)% |  |  |  |  | MI- Minor Irrigation |  |  |  | PW - Public Welfare
[27 empty] | SW- Social Welfare |  |  |  | OI - Other Infrastructure
[7 empty] | Constructions : 60% Completed | [11 empty] | D |  |  | (41 - 60)% |  |  |  |  | Under Sukitha purawara
SC -Sanitary and common facilities ( සනීපාරක්ෂක හා පොදු පහසුකම්)
[7 empty] | Constructions : 80% Completed | [5 empty] | Received goods / instruments as per the order | [5 empty] | E |  |  | (61 - 80)% |  |  |  |  | RD - Sanitary and common facilities Road and Derange Development (මාර්ග හා කාණු පද්ධති සංවර්ධනය)
MC -Maternity and Child Clinic ( මාතෘ හා ළමා සායන)
[7 empty] | Constructions : 99% Completed | [5 empty] | Completed lists of goods to be given to beneficiaries | [5 empty] | F |  |  | (81 - 99)% |  |  |  |  | SS - School and Sports (පාසල් හා ක්‍රීඩා සංවර්ධනය)
CH - Community Hall and Sewapiyasa (ප්‍රජා ශාලා හා සේවා පියස ගොඩනැගිලි සංවර්ධනය)
[7 empty] | Constructions : 100% Complete | [5 empty] | Issued goods and instruments to identified institutions/ CBOs | [5 empty] | G |  |  | 100% |  |  |  |  | RP - Religious center Developments (ආගමික මධ්‍යස්ථාන සංවර්ධනය)
[10 empty] | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600
Constructions: B - 1 = Estimates approved / Bid documents prepared, B - 2 = Quotation / Bid called B - 3 = Quotation / Bid Received B - 4 = Contract Awarded. (25% completed)

## Summary
Decentralized Capital Budget Programme -2018 - Colombo District
Physical and Financial Progress JULY 2018
| Division | COLOMBO
| Vote | 950
S.No. | Sector | No of Total Projects | Type of Project |  | Allocation (Rs.) | Total Estimate Cost (Rs.) |  | Amount of Released Allocation (Rs) |  |  | Agreement Cost (Rs) | Physical Progress (c) | [9 empty] | Financial Progress |  |  |  | No of Beneficiaries
[12 empty] | A | B |  |  |  | C | D | E | F | G | Expenditure (Work Done)(Rs) | Vat (Rs) | Admin Cost (Rs) | Total Expenditure (Rs)
|  |  | Construction | Puchersing |  | With VAT | Without VAT | Without Adm (Rs) | Admin (1.5%) (Rs) | Total (Rs) |  |  | i | ii | iii | iv
1 | SC | 4 | 4 |  | 5000000 | [6 empty] | 4 | [13 empty] | 3600
2 | RD | 4 | 4 |  | 6000000 | [6 empty] | 4 | [13 empty] | 3500
3 | MC
4 | SS | 1 | 1 |  | 2000000 | [6 empty] | 1 | [13 empty] | 1500
5 | CH
6 | RP
Total |  | 9 | 9 | 0 | 13000000 | [6 empty] | 9 | [13 empty] | 8600
* Projects should be categorized for following sectors
Sukitha purawara
SC - සනීපාරක්ෂක හා පොදු පහසුකම්
RD - මාර්ග හා කාණු පද්ධති සංවර්ධනය
MC - මාතෘ හා ළමා සායන
SS - පාසල් හා ක්‍රීඩා සංවර්ධනය
CH - ප්‍රජා ශාලා හා සේවා පියස ගොඩනැගිලි සංවර්ධනය
RP - ආගමික මධ්‍යස්ථාන සංවර්ධනය

## Sheet1
Sukitha Purawara Programme - 2018 - Colombo District
අනු අංක | ක්‍රියාත්මක බලධාරී ආයතනය | ව්‍යාපෘති සංඛ්‍යාව | වෙන් කළ මුදල (රු.) | භෞතික ප්‍රගතිය
|  |  |  | A |  |  | B | C | D | E
|  |  |  | 1 | 2 | 3
1 | ප්‍රාදේශීය ලේකම් (ඉදිකිරීම්) | 8 | 11500000 |  | 7 | 1
2 | කොළඹ නගර සභාව | 1 | 1500000 |  |  | 1
එකතුව |  | 9 | 13000000 |  | 7 | 2
| A1 - ශක්‍යතා අධ්‍යන කල |  | A2 - නාම සංශෝධන දි.ලේ යොමුකර ඇති
| A3 - ඇස්තාමේන්තු සකස්කරීමට දන්වා ඇති |  | B - ඇස්තාමේන්තු සකස්කර ප්‍රතිපාදන ගෙන්වීමට දි.ලේ යොමුකර ඇති
| C - ප්‍රතිපාදන ලබා ඉදිරි කටයුතු කිරීම |  | D -වැඩ ආරම්භකර ඇති
E - වැඩ අවසන්